## Sheet1
Dates | Weeks | Milestone | Tasks- Overview | Task-BreakDown
January 15 - January 21, 2024 | Week-0 | ProjectSetup | Project Initialization/Design/ Evaluation | Discussed with Dr.Rita Orji for reasearch project
GitHub Repo, Tech stack, flutter, python, and backend hosting
Implemented Figma design for application. UI Screen and got important feedback to rectify the issues.
January 22 - January 28, 2024 | Week-1 | User Management | Register/Singup | User Management: Register/Signup, Login, User Profile
Login
|  |  | User - Profile | Implementation of WHO BMI Calculation
WHO- Bmi implementation
|  | Dashboard | DashBoard - Front End | Dashboard Design and Frontend Implementation
|  |  | New Log Entry Front End | New Log Entry Frontend Integration
|  |  | History/Trends Front End | History/Trends Frontend Development
|  |  | Awards Page- Front End | Awards Page Frontend Setup
|  |  | Interventions/Trainer Tips - front end | Interventions/Trainer Tips Frontend Integration
January 29 - February 4, 2024 | Week - 2 | Manual Log Entry- new Meal Type(data) Entry | Back End Integration | Manual Log Entry for New Meal Type Data Entry
|  |  | Data Set Collection for Training Machine Learning - Calorie Prediction | Backend Integration for Data Entry
|  |  | Data Set pre-processing | Collection of Data Sets for ML - Calorie Prediction
Data Set Pre-processing
February 5 - February 11, 2024 | Week - 3 | Machine Learning- Training a Model | Train a ML model for calorie prediction | Training ML Model for Calorie Prediction
|  |  | Fine Tuning ML Model- by using various Validation Techniques | Fine-tuning ML Model using Various Validation Techniques
|  |  | Explore Deep Learning Techniques | Exploration of Deep Learning Techniques
Quality Assurance and Testing
February 12 - February 18, 2024 | Week-4 | Implementing Interventions/ Suggestions/Notifications System | Timely Interventions on Timely User Logging, Acheivements | Implementing Interventions/Suggestions/Notifications
|  |  | Reminders | - Timely Interventions based on User Logging and Achievements
|  |  | Self-Monitoring System | Create Real time charts
Create History on selecting the date, change the analysis of charts
February 19 - February 25, 2024 | Week-5 |  | suggest alternative food items (within the same category) with less calories | Suggest Alternative Food Items with Fewer Calories
|  |  | suggest certain exercises to burn excess calories (if user opts to consume the food) | Recommend Exercises to Burn Excess Calories
|  |  | connect users to an in-app conversational AI agent (leveraging ChatGPT or Bard) to obtain healthy dietary suggestions in real-time | Integration of In-App Conversational AI Agent for Real-time Dietary Suggestions
February 26 - March 10, 2024 | Week-6 | Detect food images and predict calories using Machine Learning techniques | Predict Calories after user upload a image | Research on Detecting Food Images and Predicting Calories using ML Techniques
Review and Optimization
March 10 - March 17, 2024 | Week -7 | Implement the ML model to auto extract required food metadata | Train ML Model | Implement ML Model to Automatically Extract Required Food Metadata
|  |  | Integrate the ML Model with Backend | Train ML Model Further if Necessary
|  |  | Front End Integration | Integration of ML Model with Backend Systems
Frontend Integration of all Features
|  |  | Deployment | Final Testing and Quality Assurance
Deployment of the Product to Production Environment
March 17 - March 26, 2024 | Week-8 | Wrap up | Made report and presentation of the
application to my supervisor Dr. Rita Orji