## Sheet1
Weeks | Module | Tasks- Overview | Task-BreakDown
Week-1 | User Management | Register/Singup | User Management: Register/Signup, Login, User Profile
Login
|  | User - Profile | Implementation of WHO BMI Calculation
WHO- Bmi implementation
| Dashboard | DashBoard - Front End | Dashboard Design and Frontend Implementation
|  | New Log Entry Front End | New Log Entry Frontend Integration
|  | History/Trends Front End | History/Trends Frontend Development
|  | Awards Page- Front End | Awards Page Frontend Setup
|  | Interventions/Trainer Tips - front end | Interventions/Trainer Tips Frontend Integration
Week - 2 | Manual Log Entry- new Meal Type(data) Entry | Back End Integration | Manual Log Entry for New Meal Type Data Entry
|  | Data Set Collection for Training Machine Learning - Calorie Prediction | Backend Integration for Data Entry
|  | Data Set pre-processing | Collection of Data Sets for ML - Calorie Prediction
Data Set Pre-processing
Week - 3 | Machine Learning- Training a Model | Train a ML model for calorie prediction | Training ML Model for Calorie Prediction
|  | Fine Tuning ML Model- by using various Validation Techniques | Fine-tuning ML Model using Various Validation Techniques
|  | Explore Deep Learning Techniques | Exploration of Deep Learning Techniques
Quality Assurance and Testing
Week-4 | Implementing Interventions/ Suggestions/Notifications System | Timely Interventions on Timely User Logging, Acheivements | Implementing Interventions/Suggestions/Notifications
|  | Reminders | - Timely Interventions based on User Logging and Achievements
|  | Self-monitoring | Reminder System Setup
|  | reward (incentivize users for logging food and engaging with interventions) | - Self-monitoring Features
Reward System Implementation to Incentivize User Engagement
Week-5 |  | suggest alternative food items (within the same category) with less calories | Suggest Alternative Food Items with Fewer Calories
|  | suggest certain exercises to burn excess calories (if user opts to consume the food) | Recommend Exercises to Burn Excess Calories
|  | connect users to an in-app conversational AI agent (leveraging ChatGPT or Bard) to obtain healthy dietary suggestions in real-time | Integration of In-App Conversational AI Agent for Real-time Dietary Suggestions
Week-6 | Detect food images and predict calories using Machine Learning techniques | RnD | Research on Detecting Food Images and Predicting Calories using ML Techniques
Review and Optimization
Week -7 | Implement the ML model to auto extract required food metadata | Train ML Model | Implement ML Model to Automatically Extract Required Food Metadata
|  | Integrate the ML Model with Backend | Train ML Model Further if Necessary
|  | Front End Integration | Integration of ML Model with Backend Systems
Frontend Integration of all Features
|  | Deployment | Final Testing and Quality Assurance
Deployment of the Product to Production Environment